## Schedule
Website Redesign — Project Schedule
Phase | Task | Owner | Start | End | Days
Discovery | Stakeholder interviews | PM | 2026-08-03 | 2026-08-07 | 5
Discovery | Analytics audit | Data | 2026-08-05 | 2026-08-12 | 8
Design | Wireframes | UX | 2026-08-13 | 2026-08-26 | 14
Design | Visual design | UI | 2026-08-24 | 2026-09-11 | 19
Build | Frontend implementation | Eng | 2026-09-07 | 2026-10-09 | 33
Build | CMS integration | Eng | 2026-09-21 | 2026-10-16 | 26
Launch | QA & accessibility | QA | 2026-10-12 | 2026-10-23 | 12
Launch | Go-live & monitoring | DevOps | 2026-10-26 | 2026-10-30 | 5